## GantChart
No. | Project Phase & Tasks | Brief description |  | planned days | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Specification
| Establishment of RS485 Communication between Danfoss IC2 drive B&R C70 Controller | Metting the Mentor - discussion about the project. | Planned | 1
Actual | bar: Week 1
Implementation
| Study about Ring Frame machine | Analyzing the Current communication system Used. | Planned | 3 | bar: Week 1
Actual | bar: Week 1
| Study about RS485 Communication | Studying the RS 485 Commuincation.(Object dictionary,SDO,PDO) | Planned | 2 | bar: Week 1 to Week 2
Actual | bar: Week 1 to Week 2
| Selecting the specifications for the hardware | Deciding the controller and IO modules for the project | Planned | 2 | bar: Week 2
Actual | bar: Week 2
| BOM Generation | Bom Creation for the Project. | Planned | 1 | bar: Week 2
Actual | bar: Week 2
| Building the software | Developing the software required for RS485 Communication using sample program. | Planned | 3 | bar: Week 2 to Week 3
Actual | bar: Week 2 to Week 3
| Connections on hardware | Connecting the modules with B&R Controller. | Planned | 2 | bar: Week 3
Actual
| IO Mapping | Create New Configuration and Mapping all the Inputs and Outputs | Planned | 1 | bar: Week 3
Actual
| Making Communication between Hardware and software | Controlling the drive according to the logic. | Planned | 6 | bar: Week 3 to Week 4
Actual
| Testing | Testing all Mapped variables. | Planned | 2 | bar: Week 4
Actual
| Making Communication between Hardware and software | Controlling the drive according to the logic. | Planned | 6 | bar: Week 4 to Week 5
Actual
| Project Analysis | Analyzing the improvement in this project for Comber communication | Planned | 3 | bar: Week 5
|  |  | Actual | 1
Testing
| Testing | Testing all the Sequence | Planned | 3 | bar: Week 6
Actual
Documentation
| Presentation | Creating PPT and Report for presentation | Planned | 2 | bar: Week 6
Actual
|  | Total |  | 38
Current Project Risks:
Other Important Notes:
Note on A2: Author: Refers to the requirement in the specification
Note on D2: Author: Brief description of the requirement
Note on F2: Author: Planning from specification